## Communication Plan
Communication Plan
Project | peer8: Peer Review Web Application
Team Members
Cole Cage - Project Manager - Developer
Jannat Saeed - Security Manager - Developer
Yhara Mendoza - Database Administrator - Developer
Cuinn Owens - Quality Assurance Manager - Developer
Noah Taylor - Development Manager - Developer
Franciso Ayala - Application Architect - Developer
ID | Communication Title | Purpose | Audience | Delivery Mode | Frequency | Start Date | End Date | Assigned Resource | Notes
C1 | Initial Meeting | Familiarize group members, create communication plan | Team Members | In Person | One-time | 2023-03-07 | 2023-03-07 | Full Team | Whole team met and described their strengths. Roles were assigned based on those strengths
C2 | Stakeholder Meeting | Initial meeting with stakeholder | Stakeholder | In Person | One-time | 2023-03-09 | 2023-03-09 | Full Team | Frequency susceptible to change after stakeholder meeting.
C3 | Biweekly Progress Meetings | Update team, report progress, troubleshoot any problems | Team Members | In Person/Online | Twice a week | 2023-03-21 | 2023-04-20 | Full Team | Team meets twice every week to discuss progress and next steps
C4 | Sprint Planning Meetings | Determine which backlog items will be handled in the next sprint | Development team | In Person | Every 2-4 weeks | 2023-03-21 | 2023-04-20 | Full Team | Will occur before starting a sprint
C5 | Sprint Review Meetings | Discuss what tasks were accomplished during the recent sprint | Stakeholder | In Person | Every 2-4 weeks | 2023-03-21 | 2023-04-20 | Full Team | Will occur after completing a sprint
C6 | Change Requests | Discuss necessary changes to features, policies, etc. | Stakeholder | In Person | As needed | TBD | 2023-04-20 | Full Team | Will occur when stakeholder presents changes that need to be addressed
C7 | Risk Management Meetings | Identify and mitigate project risks | Stakeholder | In Person | As needed | TBD | 2023-04-20 | Full Team | Address any risks that are identified and form solutions
C8 | Technical Reviews | Review technical design and code | Development team | In Person | As needed | 2023-04-13 | 2023-04-20 | Full Team | Code review before project is delivered.
C9 | User Acceptance Testing | Test project deliverables | End-users, QA | In Person/Online | As needed | 2023-04-13 | 2023-04-20 | Full Team | Test plan and test results TBD