## Backlog
Product Backlog - Master
Legends
| Priority | High, Medium, Low
| Status | Not Started, In-Progress, Complete
ID | Priority (H/M/L) | Description | Assigned Resources | Estimated Hours | Start Date | Status (NS, IP, C)
1 | H | As the faculty user, I should possess the capability to exclude a student's submission, or lack thereof, to prevent any detrimental effects on the other students' peer review results. | Developers | 1 hours | 2023-03-29 | NS
2 | H | Faculty user must be able to customize student rosters for each class. | Developers | 3 hours | 2023-03-30 | C
3 | H | Faculty user must be able to customize groups within the classes. | Developers | 2 hours | 2023-03-30 | C
4 | H | Faculty users must be able to customize peer review protocols, by crontrolling what kind of input types the student can submit. | Developers | 4 hours | 2023-03-26 | C
5 | H | Faculty user must be able to customize the peer review grading rubric. | Developers | 2 hours | 2023-03-27 | C
6 | H | As the faculty user, I should have the ability to create a reusable, customizeable template. Additionally, I should be able to select from previously used templates and assign them accordingly. | Developers | 5 hours | 2023-03-24 | C
7 | M | As the faculty user, I should be able to select previously used templates and edit them. | Developers | 2 hours | 2023-03-25 | IP
8 | H | As the faculty user, I should possess the capability to create an assignment. | Developers | 3 hours | 2023-03-24 | C
9 | H | As the faculty user, I should be authorized to make modifications to the questions as necessary. | Developers | 3 hours | 2023-04-03 | C
10 | H | As the faculty user, I should be able to receive an output of all individual reviews and final computations upon the due date. | Developers | 1 hours | 2023-03-27 | C
11 | H | As the faculty user, I should be able to assign different types of scoring ratings for different types of questions. | Developers | 3 hours | 2023-04-03 | C
12 | H | As the faculty user, I should be able to assign students to groups. | Developers | 2 hours | 2023-03-26 | C
13 | H | As the faculty user, I should be able to view all scores that students turn in for each of the peer reviews. | Developers | 1 hours | 2023-03-26 | C
14 | L | As the faculty user, I should be able to organize the peer reviews. | Developers | 1 hours | 2023-04-04 | C
15 | H | As the student user, the only people who should be able to see what a student has submitted is me and the professor. | Developers | 4 hours | 2023-03-27 | C
16 | H | As the student/faculty user, the system should be in tune with UTC's mandated by law to keep records confidential. | Security Manager | 10 hours | 2023-03-29 | C
17 | H | As the student/faculty user, I should be required to authenticate my account after logging in before I can access the application. | Security Manager | 4 hours | 2023-03-30 | C
18 | L | As the faculty user, I should be able to receive notifications for assignment submission deadlines and peer review feedback. | Developers | 30 hours | 2023-04-04 | NS
19 | M | As the faculty user, peer reviews must have a place for numerical rating but also a place for comments by students. | Developers | 4 hours | 2023-03-26 | C
20 | L | As the student user, I should be able to leave comments on questions in the peer reviews. | Developers | 2 hours | 2023-03-26 | C
21 | H | As the student/faculty user, I should be able to create an account. | Developers | 10 hours | 2023-03-25 | C
22 | H | As the student/faculty user, I should be able to have a secure login. | Developers | 10 hours | 2023-03-27 | C
23 | M | Student user should be able to edit their submission before the deadline. | Developers | 4 hours | 2023-03-30 | C