## Gantt Chart
Project Plan - Gantt Chart
Project | Peer8
Team Members:
Cole Cage - Project Manager - Developer
Jannat Saeed - Security Manager - Developer
Yhara Mendoza - Database Administrator - Developer
Cuinn Owens - Quality Assurance Manager - Developer
Noah Taylor - Development Manager - Developer
Francisco Ayala - Application Architect - Developer |  |  |  | Project Start: |  | 2023-03-07
|  |  |  | Display Week: |  | 5 |  | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22
 | time axis 2023-04-03 to 2023-05-28
Task ID | Task | Predecessor | Assigned Resource | Progress % | Duration | Start Date | End Date | time axis 2023-04-03 to 2023-05-28
T1 | Project Planning | - | Project Manager | 100% | 4 days | 2023-03-07 | 2023-03-10 | bar: 2023-04-04 to 2023-04-07
T2 | Requirements Gathering | 1 | Project Manager | 100% | 3 days | 2023-03-11 | 2023-03-13 | bar: 2023-04-08 to 2023-04-10
T3 | Design and Wireframing | 2 | Application Architect | 100% | 7 days | 2023-03-14 | 2023-03-20 | bar: 2023-04-11 to 2023-04-17
T4 | Database Design | 3 | Database Administrator | 100% | 3 days | 2023-03-21 | 2023-03-23 | bar: 2023-04-18 to 2023-04-20
T5 | Front-end Development | 4 | Development Team | 100% | 14 days | 2023-03-24 | 2023-04-06 | bar: 2023-04-21 to 2023-05-04
T6 | Back-end Development | 4 | Development Team | 100% | 14 days | 2023-03-24 | 2023-04-06 | bar: 2023-04-21 to 2023-05-04
T7 | Integration and Testing | 5,6 | Quality Assurance Manager | 100% | 7 days | 2023-04-07 | 2023-04-13 | bar: 2023-05-05 to 2023-05-11
T8 | Deployment and Release | 7 | Development Team | 100% | 3 days | 2023-04-14 | 2023-04-16 | bar: 2023-05-12 to 2023-05-14
T9 | User Acceptance Testing | 7 | Quality Assurance Manager | 100% | 3 days | 2023-04-14 | 2023-04-16 | bar: 2023-05-12 to 2023-05-14
T10 | Documentation and Training | 8,9 | Full Team | 100% | 2 days | 2023-04-17 | 2023-04-18 | bar: 2023-05-15 to 2023-05-16
T11 | Final Project Review | 10 | Full Team | 100% | 2 days | 2023-04-19 | 2023-04-20 | bar: 2023-05-17 to 2023-05-18